## Sheet1
Steps | Estimated Timeline | Coaching needs | Professional services/ Activities to Accomplish | Objective | Assessment/ Survey/Checklists
Exploration | Spring-prior to implementation year | Distance/ on site Coaching | SW-PBS Readiness Checklist, SWIS/Data Readiness, SWIS Licensing Agreement (Done by SWIS facilitator $250 per school) | Admin Intro readiness, Staff intro, Administrative Questionnaire, New School Profile, SW-PBS District & school readiness checklists , SW-PBS School Leadership Team | SWIS Readiness
Program Installation | Spring- prior to implementation year | Distance/ on site Coaching | Readiness follow-up and review, Implementation planning, Data readiness/training, leadership team development | Acquire detailed knowledge of building infrastructure regarding the 8 steps for implementation training development by reviewing school readiness documents | Administrative Questionnaire, New School Profile, SW-PBS School readiness checklist , SW-PBS School Leadership Team
Training /Tier 1 Development | August | On-site training/ Coaching | Tier 1 training Leadership Team Training SWIS Training | 8 Steps: Behavior Purpose statement, matrix, Lesson plans, Universal SW-PBS in service, Leadership Team roles/ responsibilities (blue print) Internal Coach training | Self Assessment Survey, Teacher Implementation Checklist
Initial Implementation | September | Distance Coaching | Attend Leadership Team meeting , Internal Coach support | 8 Steps: Behavior statement, lesson plans, matrix, data based decision-making | none
| October | On-site Coaching/ assessment | Leadership Team meeting/ Implementation follow-up/ Internal Coach support | 8 Steps: Data collection, Reward system, Violation system, lesson plans, data based decision-making | School-wide Evaluation Tool
| November | Distance Coaching | Leadership Team meeting/ Internal Coach support | 8 Steps: Data collection, Reward system, Violation system, lesson plans | none
| December | Distance Coaching | Leadership Team/ Internal Coach support | 8 Steps: Data collection, Reward system, Violation system, lesson plans, data based decision-making | none
| January | On site Coaching/ training/ Internal Coach support | All staff | Review 8 steps, SW-PBS Tier 1 update, classroom management | Teacher Implementation Checklist (TIC)
| February | Distance Coaching | Internal Coach/ Leadership Team | Review 8 steps, SW-PBS Tier 1 update, classroom management, action planning | none
| March | On site Coaching | Internal Coach/Leadership Team | Review 8 steps, SW-PBS Tier 1 update, classroom management, action planning | none
| April | Distance Coaching | Internal Coach/Leadership Team | Review 8 steps, SW-PBS Tier 1 update, classroom management, action planning | none
| May | On site Coaching | Internal Coach/ Leadership Team | Review 8 steps, SW-PBS Tier 1 update, classroom management, action planning | Team Implementation Checklist